## Slide 1: Name of the study
Date
Clients logo

## Slide 2: Meet the Team
Team Member | Office | Role
Sales name | CDMX | Sales Account Executive
RX 1name |  | Research Experts
RX 2 name | Provo | 
AX name |  | 
PM name | Sydney | Project Manager
BOLD = Day-to-day contact for each team/General POC

## Slide 3: Research Objectives
A&U + AA Needs Segmentation:
Objective: Define partnership decision making process + Segment needs to cover through a third party.
Brand Health:
Objective: Brand’s perception, brand funnel stage, selection drivers, strengths and opportunities versus competitors and services awareness.
Update

## Slide 4: Sample Confirmation
Screeners | Quotas | Other Assumptions
N = 700 (350 medium companies / 350 large companies) Screeners: Company size (medium and large) High-hierarchy role: C-Cuite SVP VP Director Industry (TBD) Services (current users or non rejectors of outsourcing marketing services): Data Services (analytics & strategy) Marketing Services (digital & technology) Creative Services Direct Mail Customer Care Services, Sales Services Logistics and Fulfillment Tasks | Describe any Quotas Provide definitions for any terms of art such as ‘natural fallout’ or ‘best efforts’ Age (natural fallout) (TBD) Gender (natural fallout) (TBD) Country (natural fallout) (TBD) Company size (medium and large) C-Cuite SVP VP Director Industry (TBD) Services: Data Services (analytics & strategy) Marketing Services (digital & technology) Creative Services Direct Mail Customer Care Services, Sales Services Logistics and Fulfillment Tasks | Length of Interview: 20 min IR assumed to be 41-60% Approximate number of questions: 30 Segmentation: TBD once we have the data —-------------------------------- Services included: Survey Design Survey Build (programming) Crosstabs Report (PPT ¦ Slides) Client Timezone: EST Client Email: natalia.dominguez@hartehanks.com
Update

## Slide 5: Timeline
MILESTONE | # BUSINESS DAYS | START DATE | END DATE
Project Kickoff |  | 12/Aug | 03/Nov
Survey Outline to [Harte Hanks] | +5 Business Days | 13/Aug | 19/Aug
Survey Outline Approved | +2 Business Days | 20/Aug | 21/Aug
Full Survey Draft to [Harte Hanks] | +3 Business Days | 22/Aug | 27/Aug
Survey Draft Approved | +3 Business Days | 27/Aug | 01/Sep
Survey Build (programming) | +5 Business Days | 02/Sep | 09/Sep
Link Sent to [Harte Hanks] for Review | +1 Business Days | 10/Sep | 11/Sep
OPTIONAL: Link Approved for Soft Launch | +2 Business Days | 11/Sep | 15/Sep
Soft Launch | +2 Business Days | 17/Sep | 19/Sep
Check Soft Launch Data | +1 Business Day | 22/Sep | 23/Sep
OPTIONAL: Check Soft Launch Data | +1 Business Day | 24/Sep | 25/Sep
Fielding + Scrubbing | +12 Business Days | 26/Sep | 10/Oct
Report Delivered to [Harte Hanks] | +15 Business Days | 13/Oct | 03/Nov
Report Presentation | Anytime post delivery |  | 
Follow-Ups | Up to 3 rounds of deck feedback/revisions |  | 
Update